## Sheet1
Requirements |  | Estimated Time (hrs) | Time Taken (hrs) | Status
Moving Background |  | 1 | 1 | Done
Moving Walls |  | 1 | 1 | Done
Gravity Pool at the bottom Animated |  | 2 | 2.5 | Done
Player Animations Controller |  | 3 | 3 | Done
| Running | 1 | 1
| Dashing | 1 | 1
| Shifting | 1 | 1
Creating and Object Pool |  | 3 | 3 | Done
| Enemies spawning | 1.5 | 1.5
| Power ups spawning | 1.5 | 1.5
Enemies Dropping |  | 2 | 2 | Done
Enemies Animated |  | 1 | 1 | Done
Power ups popping up. |  | 2 | 2 | Done
Power ups Animated. |  | 1 | 1 | Done
Enemies do damage. |  | 1 | 1 | Done
Power ups |  | 5 | 1 | WIP
| Health pickup | 1 | 1
| Shield Pickup | 2
| Gun Pickup | 2
High Score and Current Score |  | 2 | 2 | Done
Health bar |  | 2 | 2 | Done
Menus |  | 6 | 0 | WIP
| Main Menu | 1.5
| Options Menu | 1.5
| Settings Menu | 1.5
| Game Over Screen | 1.5
Player Movement Controller |  | 3 |  | WIP
Touch Controller |  | 3 | 3 | Done
Swiping for movements |  | 4 | 2 | WIP
| Left and right for shifting. | 1 | 1
| Up and down for dashing | 1 | 1
| Tapping for gunshot powerup | 2
Set up proper Collision between elements. |  | 5 | 0 | WIP
| Power ups do not collide with enemies. | 5
Post Processing Effects |  | 4 | 0 | WIP
| Glow | 2
| Torchlight | 2
Particle Effects |  | 7 | 0 | WIP
| Dash flames | 2
| Shift wind. | 2
| Sparks for gravity pool | 3
Sound Effects |  | 8 | 0 | WIP
| Hit by enemy. | 2
| Death | 2
| Background sound | 2
| Powerup pickup | 2
Total Hours Spent |  | 66 | 27.5 | WORK IN PROGRESS